## Sheet1
Date | Stage | Phase | Page | Change request | Status | Comments
2014-08-01 | Design | P0 | Header | increase the with of search bar | Completed
2014-08-01 | Design | P0 | Header | prefix the icons for sign-up & login links in header | Completed
2014-08-01 | Design | P0 | Home page | Ad name (Ex: Greendale) and Ad category (Ex: home stay) should be displayed in two lines one below the other and not in single line, Because both of these are different attributes. This change is applicable in the featured listing on the banner image. | Pending
2014-08-01 | Design | P0 | Home page | Can you show me how the "Category" tab looks. It should show category icon and category name | Completed
2014-08-01 | Design | P0 | Home page | "Featured Homestay in Chikmagalur" should be replaced by "Featured stay options in <Chikmagalur>" where in the value Chikmagalur is populated based on the location selected. If location is not selected then it should be "Featured stay options" | Completed
2014-08-03 | Design | P0 | Home page | Section above the map has only logo, it should also have a paragraph below the log show the "about us" content and followed should be "know more" button taking the user to "about us" page | Pending
2014-08-03 | Design | P0 | Footer | Copyright message should be left aligned | Pending
2014-08-03 | Design | P0 | Home page | Need to add one more row/section between map and footer called "Other attractions". Add link and thumb image of the tourist places and famous shops like eateries, temples, ext. When clicked on this it should take user to detial page to view more about other attractions | Pending | no need to do the desing and share it with me, take care of this feature while doing coding.